## Project Priority Matrix
| Constrain | Enhance | Accept
Scope | X
Time |  |  | X
Budget |  | X

## Risk Scoring Template
Defined Conditions for Risk Management Analysis
To create a connection that serves as local network system that would provide three health agencies and two healthcare centers the chance to have connected information in relation to the residents of the area where the said healthcare groups are located. | Relative or Numerical Scales
| Very Low - 1 | Low - 2 | Moderate - 3 | High - 4 | Very High - 5
Cost
Time
Scope
Quality
Defined Conditions for Risk Management Analysis
To establish a customized system of EHR [electronic healthcare record] for future use and reference that could help in making sure the healthcare status of the community members is in top shape. | Relative or Numerical Scales
| Very Low - 1 | Low - 2 | Moderate - 3 | High - 4 | Very High - 5
Cost
Time
Scope
Quality

## Risk Mgmt Analysis Template
RISK EVALUATION
Risk | Probability | Cost | Schedule | Scope | Quality | Risk Score | Justification
Conflicting interests among leadership | 55% | 4 | 3 | 2 | 3 | 6.6 | Shareholders can drive capability. All should be inline with the requirements and will be conducting UAT
Meeting Security Requirements | 30% | 5 | 4 | 5 | 5 | 5.7 | Security is paramount and needs to have strick adherence considering the type of data that will be transferred.
No backup plan | 25% | 3 | 5 | 5 | 5 | 4.5 | If the worst occurs and the project has bugs there must be a back to continue doing business.
Scope of Design is not understood among stakeholders | 40% | 2 | 3 | 3 | 3 | 4.4 | Assumptions would hinder the process and everyone including shareholders, stakeholders and the project team must fully understand the project.
Incomplete Cutover plan | 30% | 4 | 2 | 5 | 3 | 4.2 | Transitioning from a legacy system to the new system (New LAN/EHS systems) will required detailed planning and assignment of those tasks.
Timeframe to develop according to Scope | 30% | 1 | 5 | 5 | 1 | 3.6 | Time is a risk to ensure the project is accomplished on time.
Understanding all test cases and functionality | 25% | 1 | 2 | 5 | 1 | 2.25 | Testing the requirements is more than testing for a pass. The system must also be tested to break and find weaknesses.
Lack of Resources (Technical/Business Talent) | 10% | 4 | 3 | 3 | 4 | 1.4 | Resource constraints would hinder time and impact budget.
Appropriate Designer Talent | 15% | 2 | 3 | 1 | 3 | 1.35 | The right person doing the right job. The teams currently have the talent in place.
Defined Test Plans | 10% | 2 | 2 | 2 | 5 | 1.1 | Defining the test plans will find areas that do not work or have bugs.
NOTE: This form will suffice for showing the RISKS, the Risk Scores and the Order of Risks…

## Risk Response Template
Risk Response Matrix
Risk Event | Response* | Contingency Plan | Trigger | Person Responsible | Project Lifecyle
Conflicting interests among leadership | Eliminate | Coordinated Leadership reviews | During requirements definition | Project Manager | Initiating
Meeting Security Requirements | Eliminate | Coordinate Security/Development teams to outline defined requirements | The design discussions | Project Manager | Executing
No backup plan | Mitigate | Develop failover plan to back out if implementation fails | During Planning Phase | Project Manager | Closing
Scope of Design is not understood among stakeholders | Transfer | Defined Scope Statement/Documentation/Toll Gate reviews | During Toll Gates | Project Manager | Initiating
Incomplete Cutover plan | Mitigate | Practice Cutover on other IT environments/ Dry run responsibilities | User Acceptance | Integration Team Lead | Monitoring and Controlling
Timeframe to develop according to Scope | Share | Scope/Schedule/Quality Mtgs with leadership | During Project Initiation | Project Manager | Executing
Understanding all test cases and functionality | Mitigate | Review requirements with end users/ Perform Pilot testing with SME's | During the move from QA to Production | Development Engineer | Monitoring and Controlling
Lack of Resources (Technical/Business Talent) | Accept | Create WBS-Assign Resources | During the Planning Phase | Project Manager | Executing
Appropriate Designer Talent | Accept | WBS | During project initiation | Project Manager | Executing
Defined Test Plans | Mitigate | Document all test/user cases to create test plan | During the move from QA to Production | End Users | Monitoring and Controlling
* = Eliminate, Mitigate, Share, Transfer, Accept